## 2015
# | Tool | Description | Type | Reported | Ticket | Feedback
1 | OmegaT | Incorrect display of RTL segments in the Fuzzy Matches pane | BUG | Yes | https://sourceforge.net/p/omegat/bugs/558/ | Didier: can be fixed
2 | Okapi | Filter configuration file is not multiplatform | BUG | Yes
3 | OmegaT | Same colors for auto and enforce matches | BUG | Yes |  | Didier: €500
4 | OmegaT | Direction of Arabic text in fuzzy matches
other bidi issues?
Long segments in Arabic not wrapped in the Fuzzy Matches pane (therefore not readable)
|  | Add TA notes to XLIFF-based projects |  |  |  | get notes from excel, add them to project_save
| OmegaT | Open zipped project from OmegaT withouth unzipping first | RFF
| OmegaT | Segment number per file?

## 2022
Created | # | Tool | Title | Type | Status | Developer | Cost | Comments | Resolved
TOTAL 2024 |  |  |  |  | WIP |  | 422.5
2024-09-28 | #274 | Okapi plugin | Translated and final segments in XLIFF 2.0 | BUG | Open! | Denis?
2024-07-15 | #273 | Okapi plugin | Filter plugin v. 1.13-1.45 breaks backward compatibility for ID-bound alternative translations | BUG | Open!
2024-07-15 | #272 | Okapi plugin | Filter plugin v. 1.13-1.45 breaks backward compatibility for tags | BUG | Open!
2024-07-10 | #1754 | OmegaT | Let user decide the maximum number of TM matches displayed | RFE | Open!
2024-06-26 | #1752 | OmegaT | Dynamic subfilter in text search results | RFE | Open
2025-05-07 | #1745 | OmegaT | Enforced translations are read-only | RFE | Open! | Thomas
2024-04-29 | #1743 | OmegaT | Commit specified files on SAVE or COMPILE | RFE | Open!
2024-04-12 | #1258 | OmegaT | "This is a Subversion repository" if wrong password on AWS repo | BUG | Open
2024-04-08 | #271 | Okapi plugin | Extraneous tags which are not escaped in XML target file | BUG | Resolved | Denis | 422.5
2024-03-14 | #2 | OmegaT 5.7.2 | Tag issues check does not flag missing tags in NEXT repetitions | BUG | Open | Thomas
2024-03-12 | #1349 | Okapi | OpenXML: equations not extracted | RFE | Open
TOTAL 2023 |  |  |  |  | WIP |  | 2502.5
2023-11-08 | #1725 | OmegaT | Trim authentication details in team projects | RFE | Open!
2023-10-31 | #1724 | OmegaT | Block creation of target files only if the SELECTED issues are found | RFE | Open!
2023-10-24 | #1722 | OmegaT | console-translate mode (CLI) to download mapped files | RFE | Open
2023-11-06 | #1226 | OmegaT | Target files include recent edits in enforced translations | BUG | Open!!!
2023-11-03 | #1225 | OmegaT | List of issues stays hidden in the background | BUG | Open!
2023-10-14 | #1720 | OmegaT | Download team project with shallow history | RFE | Open |  |  | Kos to follow up
2023-09-30 | #1323 | Okapi | Protected entries in XLIFF show translation as source text | BUG | Open |  |  | Kos to follow up. Marked as resolved: RE-TEST
2023-09-01 | #30 | OmegaT | Protect segment based on XLIFF status | RFE | Open | Thomas |  | Stax XLIFF filter
2023-08-31 | #1712 | OmegaT | Remove old buggy "Resolve conflicts" dialog (and keep the new "Merge" one) | RFE | Open
2023-08-31 | #1215 | OmegaT | Protected entries in XLIFF show translation as source text | BUG | Open
2023-08-07 | #1214 | OmegaT | Extraneous tags which are not escaped in XML target file | BUG | Transfered |  |  | transferred to okapi-plugin#271
2023-08-07 | #1213 | OmegaT | Selection of match for pre-translation varies through different OS's | BUG | Resolved
2023-08-07 | #1212 | OmegaT | Random selection of match for pre-translation depending on TMX file paths | BUG | Resolved | Briac
2023-07-05 |  | OmegaT | Adapt customization script to work in version 6.1 |  | Resolved | Briac/Gergoe | 390 | no ticket – request by email
2023-07-17 | #1202 | OmegaT | Error 403 when accessing different repo with different creds in same domain | BUG | Open! |  |  | Marked as fixed: RE-TEST
2023-07-12 | #27 | tmx comments provider | T&A notes: T&A note is "null" if the target language doesn't match | RFE | Open! | Thomas? |  | Marked as fixed: RE-TEST
2023-07-12 | #26 | tmx comments provider | T&A notes: source text in notes/notes.tmx used as the note | RFE | Open! | Thomas? |  | REVIEW
2023-07-11 | #1201 | OmegaT | -1 instead of repo name in repository credentials | BUG | Open! |  |  | REVIEW
2023-07-11 | #1200 | OmegaT | Closing a new project does not register pre-populated translations | BUG | Open! | Thomas?
2023-07-03 | #1708 | OmegaT | Improve colors in the list of project files | RFE | Open
2023-06-27 | #1185 | OmegaT | Saving does not register pre-translation in new projects | BUG | Open!! | Thomas?
2023-06-17 | #11 | plugin-omt-package | NoClassDefFoundError when packing project in OmegaT 6.1.0 | BUG | Resolved | Briac | 130 | https://github.com/omegat-org/omegat/pull/646 | 2023-07-23
2023-05-23 | #1309 | Okapi | XML filter does not extract resname if unit contains HTML block-level tags | BUG | Resolved? | Denis/Briac | 325 | https://bitbucket.org/briacp/omegat-plugin-jdk8-patched/branch/fix/capstan/incorrect-name-with-tags | ?
2023-05-23 | #1176 | OmegaT | The COMPILE event is fired *after* the target commit | BUG | Resolved | Briac | 97.5 | https://github.com/omegat-org/omegat/pull/609
2023-05-18 | #1171 | OmegaT | Enforced translations lose background color | BUG | Open
2023-05-03 | #1164 | OmegaT | Auto-populated translations disappear when a segment gets activated | BUG | Resolved | Thomas | 357.5 | Marked as fixed. Fixed in 5.7.2, TEST IN 6.0 | Started by Briac, handed over to Thomas: https://github.com/omegat-org/omegat/pull/645
2023-05-03 | #9 | plugin-omt-package | Add property in config to remove mappings (to pack as offline project) | RFE | Resolved | Briac | 97.5
2023-04-28 | #1163 | OmegaT | Project not loaded if it contains DTD internal entities | BUG | Resolved | Briac
2023-04-24 | #1161 | OmegaT | "Set empty translation" does not work in XML file | BUG | Open
2023-04-12 | #1690 | OmegaT | "Commit target files" also commits stats file to repo | RFE | Resolved | Thomas | €120.00 | backported to 5.7.2
2023-03-11 |  | Okapi plugin | Backported latest Okapi plugin to JDK 8 |  | Resolved | Briac | 130
2023-03-22 | #1155 | OmegaT | Option "Insert the source text" enabled on its own | BUG | Resolved | Thomas
2023-03-08 | #1150 | OmegaT | Tags cannot be deleted in RTL languages | BUG | Open!! | Alex?
2023-03-08 | #1151 | OmegaT | Tag drag-and-drop duplicates tag in RTL text | BUG | Open!! | Alex?
2023-03-06 | #1200 | Okapi | XML filter adds tags arounb nnbsp by default | BUG | Open+ | Denis
2023-02-24 | #1681 | OmegaT | Straight quotes match curly quotes | RFE | Open
2023-02-16 | #51 | Okapi plugin | Translation displayed as source text if state="final" with Okapi XLIFF filter | BUG | Open! | Denis?
2023-02-15 | #1142 | OmegaT | Translation displayed as source text if state="final" with Okapi XLIFF filter | BUG | Invalid |  |  | Same as okapi ticket #51
2023-02-13 | #8 | plugin-omt-package | Only __DEFAULT__ project folders are packed correctly | RFE | Open
2023-02-10 | #1674 | OmegaT | Remove custom tags issues and flagged text from mandatory tag check | RFE | Open!
2023-02-07 | #1672 | OmegaT | Hide tag-only segments | RFE | Open!! | Thomas | 195
2023-01-26 | #1669 | OmegaT | Remove leadinga and trailing tags with Okapi filters | RFE | Open!! | Thomas
2023-01-26 | #1670 | OmegaT | Reuse credentials in team projects | RFE | Resolved | Thomas | 65
2023-01-23 | #1184 | Okapi | Fractions in Word file are not extracted | BUG | Open! | Denis
2023-01-22 | #49 | Okapi plugin | Use resname as segment identifier (instead of correlative number) | RFE | Resolved | Briac | 585 | PR: https://bitbucket.org/okapiframework/omegat-plugin/pull-requests/20
2023-01-20 | #1140 | OmegaT | Context-bound matches are ignored in /tm/auto | Bug | Resolved | Briac | 130
2023-01-03 | #1132 | OmegaT | OmegaT CLI gets stuck at missing empty folders when run on team project | Bug | Open!
TOTAL 2022 |  |  |  |  | WIP |  | 4087.5
2022-11-14 | #1125 | OmegaT | OmegaT's main window is sent to unplugged monitor | Bug | Open
2022-10-24 | #1641 | OmegaT | Navigate between segments inserted from /tm/auto and /tm/enforce | RFE | Open | Kos |  | Marked as fixed: RE-TEST / back-port?
2022-10-21 | #1124 | OmegaT | Local project does not update after remote masking some files | Bug | Open!! |  |  | Marked as fixed: RE-TEST / back-port?
2022-10-10 | #1122 | OmegaT | Tag color is obfuscated if target language uses RTL script | Bug | Open? |  | 32.5
2022-07-15 | #43 | Okapi plugin | Tag tooltips do not show the locked text | Bug | Resolved | Denis | 1360 | Denis has opened a pull request #16 for it and sent a manual build of plugin with Okapi dependency at c5fa867 commit. To be tested.
373466 | #1622 | OmegaT | Option to give or revoke full writing access to team project users | RFF | Open
2022-07-01 |  | OmegaT | scripts and support with scripting |  | Resolved | Kos | 330 | No ticket
2022-06-28 | #38 | Okapi plugin | OpenXML filter for OmegaT gives error when opening Excel file with embedded HTML | Bug | Open! |  | 1000 | Quote TBC. Re-test with latest version of Okapi plugin. Transferred from Okapi issue #1020.
2022-06-27 | #1621 | OmegaT | Add notes as `<note>` in target XLIFF file | RFF | Open! | Thomas |  | Green light pending
2022-05-12 | #1616 | OmegaT | Non-unique IDs when segmenting text blocks extracted by Okapi OpenXML | RFE | Open! | Thomas
2022-05-14 | #37 | Okapi plugin | HTML sub-filter in JSON filter not working in OmegaT | Bug | Resolved | Denis |  | Blocking issue for translation JSON files with embedded HTML content in OmegaT. Same as OmegaT #1097. Fixed by Denis Konovalenko in June 2022 (cost: 540, payable by ACER). However, deployment issues remain because Okapi has dropped support for Java 8 while OmegaT is not shipped yet with JRE for Java 11. The patched plugin does not work with OmegaT unless OmegaT is run with Java 11, which therefore needs to be installed manually and OmegaT configured to run with that version.
2022-04-08 | #36 | Okapi plugin | Alternative translations do not work for repetitions within paragraphs | Bug | Open! | Denis? | 40 | Same as OmegaT #1616, not clear whether this needs to be fixed in OmegaT or in the Okapi filter or in both.
2022-05-31 | #1101 | OmegaT | No ID-bound matching in /tm/tmx2source | RFE | Resolved? | Thomas | 0 | Marked as fixed: RE-TEST
2022-05-24 | #1099 | OmegaT | Absolute paths used in search results from TMs | Bug | Resolved | Hiroshi |  | Minor improvement to save space and see more clearly where matches come from. Hiroshi fixed it.
2022-05-24 | #1098 | OmegaT | The "file names" option does not work in search results from TMs | Bug | Resolved | Hiroshi |  | Hiroshi fixed it.
2022-05-12 | #1617 | OmegaT | handling ID-bound alternative translations more efficiently | RFE | Open |  |  | Originally reported as Okapi 1106.
2022-03-02 | #1092 | OmegaT | Enforced ID-bound alternative translations not recognized | Bug | Resolved |  |  | With Aaron's tips I could find the issue and propose a fix. Fixed in 5.8.1.
2022-02-22 | #1128 | Okapi | Table filter: Merge step does not keep edited translation | Bug | Open! |  |  | Online exchange at https://groups.google.com/g/okapi-users/c/lBo0LRASJyA/m/viK3SfsiBAAJ?utm_medium=email&utm_source=footer
2022-02-21 | #1090 | OmegaT | Fails to load TM using `<ph>` tags | Bug | Open |  |  | Marked as fixed: RE-TEST
2022-02-16 | #1608 | OmegaT | Add notes to the translator in /tm/notes/foo.tmx | RFF | Resolved | Thomas | 260 | This would be necessary (or very handy) in projects where we need to use second source for a reference version, and it would be confusing to use the same space for translation notes.
2022-01-19 | #35 | Okapi plugin | Improve tags conversion to match OmegaT tags better | RFE | Open? |  |  | Online discussion: https://groups.google.com/g/okapi-users/c/de5LTH7hP4g/m/PysP0msQBwAJ?utm_medium=email&utm_source=footer
-
2021-09-24 | #1070 | OmegaT | Unexpected enforced translation (first match) in OmegaT 4.3 | Bug | Open
2021-09-21 | #1592 | OmegaT | Option to choose how matches are sorted (asc or desc) | RFE | Open~ |  |  | @todo: write specs
2021-09-21 | #1591 | OmegaT | Option to export project's master TMs when pressing Ctrl+D | RFF | Resolved
2021-06-25 | #1578 | OmegaT | Do not propose source text as match from other languages | RFF | Open |  |  | Marked as fixed: RE-TEST
2021-05-10 | #41 | Okapi plugin | Unable to set `<EMPTY>` translation in OmegaT with Okapi filter OpenXML | Bug | Open? |  |  | Transferred from Okapi issue #1055
2021-05-09 | #42 | Okapi plugin | Error parsing XML content (with OpenXML filter in OmegaT) | Bug | Open! | Denis | 480 | Transferred from Okapi issue #1054
2021-05-09 | #1566 | OmegaT | Replace glossary hits when inserting fuzzy match | RFF | Open
2021-05-05 | #1565 | OmegaT | Give each segment a unique ID | RFE | Open!! |  |  | Very important, lack of unique segment ID is a common source of support requests and we spend a great deal of time tweaking source files to allow the creation of alternative translations. The problem is mitigated whenever we can use an Okapi filter (OpenXML, HTML, etc.) but Okapi filters sometimes have other issues
2021-04-30 | #1046 | OmegaT | Glossary has wrong encoding for non-ASCII characters | Bug | Rejected
2021-03-24 | #1559 | OmegaT | Validate tags when leaving a segment only for that segment | RFF | Open!
2021-03-02 | #1038 | OmegaT | "Remove leading/trailing tags" removes tags that are not a tag pair | Bug | Open
2021-02-16 | #1037 | OmegaT | Next Unique Segment shortcut conflicts with Log Out on Mac | Bug | Open
2021-02-04 | #1020 | OmegaT | OpenXML filter for OmegaT gives error when opening Excel file with embedded HTML | Bug | Transfered |  |  | Re-test with latest version of Okapi plugin.
2021-01-22 | #1032 | OmegaT | OmegaT ignores system variable %appdata% on Windows | Bug | Open
2021-01-20 | #1546 | OmegaT | Include OMT plugin in the vanilla installation | RFF | Open! | Thomas | 390 | Quote
2020-12-10 | #1027 | OmegaT | Resolve Conflicts dialog is useless when enforced matches are updated | Bug | Open |  |  | This feature request aims at preventing the problem that users might inadvertedly create bilingual target files (mixing text in the source and the target languages) if they leave some segments untranslated. OmegaT should not opinionatedly use the source text as the translation if the segment is not translated.
2020-12-10 | #1529 | OmegaT | Folder scripts/application_close to run scripts when OmegaT closes | RFF | Open
-
2020-11-27 | #1527 | OmegaT | Do not export untranslated segments | RFE | Open
2020-11-13 | #558 | OmegaT | Incorrect display of RTL segments in the Fuzzy Matches pane | Bug | Open
2020-11-11 | #1005 | Okapi | XLIFF filter (for OmegaT) hides files with DOCTYPE including URL | Bug | Invalid |  |  | Not reproduceable
2020-10-28 | #1020 | OmegaT | Project file filters are not preserved | Bug | Open
2020-09-29 | #993 | Okapi | Okapi XLIFF filter for OmegaT registers/expects segment IDs that break ID-bound matches | Bug | Open
2020-09-21 | #1520 | OmegaT | Two many locations for user-added plugins | RFE | Rejected |  |  | Closed by the dev team lead (Aaron) with the argument that the two locations are necessary.
2020-09-21 | #1519 | OmegaT | OmegaT uses wrong/old version of plugin in case of conflict | RFE | Resolved |  | 195 | https://github.com/omegat-org/omegat/pull/646 | 2023-07-26
2020-08-14 | #969 | Okapi | Resname (from XLIFF) appears in the comment field in OmegaT | RFE | Open~ |  |  | Several details could be optimized in the Comments pane vs Segment Properties pane: resname, ID, comment, etc. Test with JSON to XLIFF roundtrip.
2020-07-16 | #1003 | OmegaT | Matches containing non-alphabetical text are ignored in TM leverage | Bug | Resolved | Briac | 0 | Could be fixed with diff-patch-match plugin. WIP with mock-up script.
2020-08-21 | #1015 | OmegaT | Matches ignored if the two locales have the same language subtag | Bug | Open |  |  | Update (2022_06-24): re-test in version 5.8.0.
2020-07-16 | #1002 | OmegaT | Choice of GUI language during re-installation is ignored | Bug | Resolved
2020-07-04 | #1471 | OmegaT | "Full segment" option in search dialog | RFE | Open
2020-06-28 | #1497 | OmegaT | Automatically create system-wide TM repository | RFF | Open |  |  | ticket, + discussion + new discussion -> new ticket??? first wait and see, nothing happened -> then propose sponsorship writing: script to save reading: looking for developer
2020-06-13 | #947 | Okapi | OpenXML Filter: improve the segmentation quality and merge with complex script formatting | RFE | Open |  |  | Marked as resolved: RE-TEST
2020-04-27 | #933 | Okapi | OpenXML filter: formatting issues in Arabic translation (RTL) | Bug | Resolved |  |  | On hold, TBC whether Word is the formatting for coding guides in PISA25. As soon as it's confirmed, this ticket would have highest priority.
2020-04-26 | #932 | Okapi | Hook for OmegaT translation kit not working anymore | Bug | Open! |  |  | Follow up with this.
2020-04-15 | #931 | Okapi | OpenXML Filter: remove redundant BIDI properties clarification in RTL | RFE | Open
2020-04-08 | #987 | OmegaT | "Use as default translation" does not work | Bug | Open
2020-03-01 | #988 | OmegaT | RLE and LRE control characters not visible in editor | Bug | Resolved
2020-02-24 | #982 | OmegaT | Layout issues in target Word files in Arabic | Bug | Open
2020-01-27 | #979 | OmegaT | Arabic fuzzy matches not wrapped in FM pane | Bug | Open
2020-01-27 | #977 | OmegaT | Character and tag are glued together in Arabic | Bug | Open
2020-01-22 | #975 | OmegaT | ID-binding context damaged with Olifant-edited TMX files | Bug | Open
2019-04-29 | #1445 | OmegaT | Multiple-value input/editor for custom tags | RFF | Open
2019-04-29 | #1444 | OmegaT | Enhancing number update when inserting fuzzy matches | RFF | Open
2019-03-16 | #1427 | OmegaT | Project-specific custom tag definition | RFF | Open |  |  | See #926 Make Regular expression for custom tags project-specific
-
2018-04-13 | #23 | Okapi plugin | Translation registered as same as source not taken into account | Bug | Open! | Kuro
2018-04-13 | #22 | Okapi plugin | Segment set as `<EMPTY>` not empty in XLIFF | Bug | Fixed? | Kuro
2017-04-17 | #18 | Okapi plugin | Set the state of the target to 'translated' when saving | RFE | Open! | Kuro? |  | ON HOLD, REVIEW
2016-03-28 | #1207 | OmegaT | Treat custom tags as OmegaT tags when calculating match estimates | RFF | Open
2006-11-07 | #245 | OmegaT | Formatting shortcuts | RFE | Open |  |  | Created by Henry Pijffers

## ETS
# | Tool | Project | Subject | Description | Reported | Onboarded | Confirmed